## Sheet1
Pygame game
Goal | Make a 2D platformer side-scroller game in Python using Pygame library, containing menu, configurations and two levels
More information | General | The goal of the game is to cross the levels, avoiding obstacles. The graphics elements resolution will be 640 x 360. The game should run in Windows, Linux and Mac.
| Menu | Contains buttons for next screen selection, game or configuration. It also has a background art.
| Levels | The level part contains the gameplay, implementing elements like the player, the ground and the obstacles.
| Configuration | Contains buttons for the user define technical aspects like resolution, enable fullscreen and vsync.
Tools | Programming | Python3
Pygame
Vim
Git (Github)
| Art | Paint.net
| Project | Trello
Timeline | 2018-12-25 | Beginning of the project
| 2019-01-01 | Install tools used and study Pygame tutorials
| 2019-01-08 | Build general code structure and develop menu
| 2019-01-15 | Develop configurations
| 2019-01-22 | Develop levels
| 2019-01-29 | Art
| 2019-02-05 | Completion
Planned time | From 15 to 20 hours / week
Planning (Portuguese) | https://trello.com/b/2jGfgnP1/jogo-em-pygame
Code | https://github.com/marcelohbarros/Pygame_game